## Sprint Schedule
Date | Schedule | Deliverable
2024-09-18 | Sprint 0 | Setting up the project and proposal.
2024-10-02 | Sprint 1 | Create Initial application.
2024-10-09 |  | Create MongoDB database and schema.
2024-10-16 |  | Create header and footer.
2024-10-23 | Sprint 2 | Discover page and my planner system.
2024-10-30 | First Demo | Demonstrate progress.
2024-11-06 | Sprint 3 | Make a post functionality and user profile view.
2024-11-13 | Second Demo | Demonstrate progress.
2024-11-20 | Sprint 4 | Extra features and testing.
No class- Thanksgiving
2024-12-04 | Final Demo | Demonstrate final progress.